## Sheet1
ID | Type | Description | Owner | Impact | Probability (Risks only) | Priority | Status | Actions / Mitigation | Target Date
R-001 | Risk | Project go-live could be delayed if integration fails. | Alice Smith | High | Medium | High | Open | Schedule integration tests earlier in the timeline. | 2024-07-15
A-001 | Assumption | Vendor will deliver required hardware on time. | Bob Lee | Medium |  | Medium | Agreed | Check-in with vendor weekly. | 2024-07-01
I-001 | Issue | Key resource has resigned, causing project delay. | Diana Roy | High |  | High | In Progress | Find replacement and redistribute workload. | 2024-06-25
D-001 | Dependency | Approval from legal needed before contract signing. | Carlos Kim | High |  | Critical | Pending | Follow up for approval before end of month. | 2024-06-30