## Sheet1
Project Name | Project Manager | Date | Lesson Category | Description of Lesson Learned | What Went Well | What Could Be Improved | Recommended Actions | Responsible Person | Status
Website Redesign | Jane Smith | 2024-05-10 | Planning | Defined project scope early, reduced confusion. | Early scope definition helped team focus. | More stakeholder input needed. | Engage all stakeholders at project start. | Jane Smith | Completed
Website Redesign | Jane Smith | 2024-05-10 | Execution | Delay in content delivery affected timeline. | Team adapted to changes quickly. | Content delays not anticipated. | Set clear deadlines with content providers. | John Brown | Pending